## Sayfa1
Activity No | Activity | Budget | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 5 | Quarter 6 | Quarter 7 | Quarter 8 | Quarter 9 | Quarter 10 | Quarter 11 | Quarter 12
2 | Architectural Projects | 500000 |  | 500000
3 | Static Projects | 400000 |  | 400000
4 | Technical Projects | 600000 |  | 600000
5 | Interior Design Projects | 500000 |  | 500000
8 | Land Improvements | 8000000 |  |  | 8000000
9 | Groundworks | 12000000 |  |  |  | 12000000
10 | Isolation Works | 35000000 |  |  |  |  | 35000000
11 | Load-Bearing Wall Works | 60000000 |  |  |  |  | 45000000 | 15000000
12 | Steel Construction | 45000000 |  |  |  |  | 30000000 | 15000000
13 | Levelling | 60000000 | [5 empty] | 30000000 | 30000000
15 | Roof Works | 20000000 | [7 empty] | 20000000
16 | Wood Works | 30000000 | [8 empty] | 30000000
17 | To Engineer Internal Partitions | 30000000 | [8 empty] | 30000000
19 | Pre-Definition | 200000 |  | 100000 | 100000
24 | Designing of System Components | 1500000 |  |  |  | 500000 | 1000000
25 | Integration of Components | 1000000 | [5 empty] | 1000000
27 | Production of Components | 8000000 | [6 empty] | 5000000 | 3000000
28 | Integration | 4000000 | [7 empty] | 4000000
29 | Testing and Coming Up Ready for Usage | 300000 | [8 empty] | 150000 | 150000
32 | Ambulances | 3000000 | [10 empty] | 3000000
33 | Elevators | 17000000 | [7 empty] | 7000000 | 10000000
34 | Air – Conditioning | 7000000 | [7 empty] | 3000000 | 4000000
35 | Fire Equipments | 3000000 | [10 empty] | 3000000
37 | X-Ray Devices | 22000000 | [9 empty] | 22000000
38 | Labrotarty Test Devices | 4000000 | [9 empty] | 4000000
39 | Ultrasound Devices | 2000000 | [9 empty] | 2000000
40 | Blood Test Devices | 2000000 | [9 empty] | 2000000
42 | Administrative Personnel | 480000 |  |  |  |  | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
43 | Technical Personnel | 525000 | [7 empty] | 75000 | 75000 | 75000 | 75000 | 75000
44 | Medical Personnel | 450000 | [9 empty] | 150000 | 150000 | 450000
BAC |  | 378455000 |  |  | 8100000 | 500000 | 111060000 | 61060000 | 35060000 | 37135000 | 74285000 | 30435000 | 6285000 | 585000
COMMUTATIVE TOTAL |  |  |  | 2100000 | 10200000 | 10700000 | 121760000 | 182820000 | 217880000 | 255015000 | 329300000 | 359735000 | 366020000 | 366605000